## Project Roadmap
AI PRODUCT ROADMAP & POC IMPLEMENTATION PLAN
¦-> Milestone 1 - Local Implementation
Task ID | Simplified Task Name | POC Details & Work Description | Dependencies | Est. Days (POC) | ETA Timeline | Acceptance Criteria
M1-01 | Initial Setup & Architecture Plan | Review current prototype code, list what's missing, and create a checklist of tasks to build the MVP locally. | None | 1 | Week 1 | Clear gap checklist and target architecture diagram.
M1-02 | Clean & Format Codebase | Set up code auto-formatting (Black/Ruff), type checks, and clean folder conventions so everyone writes clean code. | M1-01 | 1 | Week 1 | Code checks run cleanly with zero lint/formatting errors.
M1-03 | Project Folder Organization | Organize code into simple folders: frontend, backend, tests, configs, and helper scripts. | M1-01 | 1 | Week 1 | Folder structure created and app runs locally without broken imports.
M1-04 | Central App Settings (.env) | Store database passwords, API keys, and feature toggles in central config files (.env) instead of hardcoding. | M1-02 | 1 | Week 1 | App loads settings dynamically without hardcoded local paths.
M1-05 | Basic API Gateway Setup (FastAPI) | Create standard FastAPI server with basic API routes, `/health` check endpoint, and simple error handling. | M1-03 | 2 | Week 2 | API server starts up and responds to health and test chat endpoints.
M1-06 | Module Breakdown (Services) | Separate code into clear modules: API, AI Agents, Memory, Database, and Security tools. | M1-03; M1-04 | 2 | Week 2 | Each module is in its own file/folder with clear function calls.
M1-07 | Chat API Structure & Error Handling | Define clean JSON formats for AI requests/responses, request IDs, streaming, and user-friendly error messages. | M1-05 | 2 | Week 2 | API returns structured responses and readable error messages for bad inputs.
M1-08 | Unique ID System (Threads & Sessions) | Add unique ID generation (UUIDv7) so every chat session and message thread can be tracked easily. | M1-06; M1-07 | 1 | Week 2 | Every new chat session gets a unique time-ordered ID tag.
M1-09 | Recent Chat History (Short-Term Memory) | Keep the last N messages in active memory so the AI remembers the immediate conversation while managing token limits. | M1-08 | 2 | Week 3 | AI answers based on recent history without exceeding context limit.
M1-10 | User Memory & Preferences (Long-Term Memory) | Store user preferences and key facts in a database so AI remembers context across sessions. | M1-08; M1-09 | 2 | Week 3 | AI retrieves user background/preferences saved in earlier chats.
M1-11 | Auto Chat Summarization | Automatically compress long chat histories into a short summary so the AI doesn't forget context. | M1-09; M1-10 | 2 | Week 3 | Old chats are summarized into key points to keep AI smart & cheap.
M1-12 | Database Storage Setup (SQLite/Postgres) | Set up local database tables for saving chats, users, and logs with automated table migration scripts. | M1-08; M1-09 | 2 | Week 3 | Data remains intact after app restart and database schema updates easily.
M1-13 | AI Model Switching Layer | Build a simple connector layer to switch between different AI models (OpenAI, Anthropic, local LLM) effortlessly. | M1-06; M1-07 | 2 | Week 4 | Can switch AI models using a simple config setting.
M1-14 | Tool Connection Gateway | Allow AI agents to run tools (e.g. search database, send email) safely with input validation. | M1-06; M1-13 | 2 | Week 4 | AI can trigger external functions cleanly and safely.
M1-15 | AI Guardrails & Security Checks | Filter toxic content, hide private user data (PII like phone/email), and block prompt injection hacks. | M1-07; M1-13; M1-14 | 2 | Week 4 | Malicious/unsafe prompts are blocked and sensitive info is masked.
M1-16 | Agent Behavior Upgrades | Improve AI agent prompts to handle missing info gracefully, ask follow-up questions, and route to humans if stuck. | M1-09; M1-13; M1-14; M1-15 | 3 | Week 5 | Agents handle edge cases and clarify confusing user requests.
M1-17 | Document Search Setup (RAG Baseline) | Upload PDF/text documents, convert to vector embeddings, and retrieve relevant chunks when user asks questions. | M1-04; M1-13; M1-15 | 3 | Week 5 | AI provides accurate answers sourced directly from uploaded documents with citations.
M1-18 | Background Tasks & Caching | Cache frequent AI answers in memory (Redis) and run heavy background tasks without slowing down the UI. | M1-08; M1-12 | 2 | Week 5 | Repeated queries load instantly from cache.
M1-19 | Simple Web UI Integration | Build/connect a clean web chat user interface with loading spinners, thread history, and simple message layout. | M1-05; M1-07; M1-08 | 3 | Week 6 | User can open browser, chat with AI, see sources, and view past chats.
M1-20 | Local Testing & Documentation | Write unit tests for core features and write a simple README setup guide for new developers. | M1-02 through M1-19 | 2 | Week 6 | Tests pass locally and a new developer can setup the app in <15 mins.
38
¦-> Milestone 2 - Cloud & Infrastructure Setup
Task ID | Simplified Task Name | POC Details & Work Description | Dependencies | Est. Days (POC) | ETA Timeline | Acceptance Criteria
M2-01 | AWS Cloud Architecture Plan | Map local code components to AWS services (ECS, S3, DynamoDB, Bedrock) for cloud deployment. | M1-20 | 2 | Week 7 | Visual architecture map showing how local code runs on AWS.
M2-02 | AWS Accounts & Basic Infra Setup | Set up AWS accounts (Dev/Staging), basic VPC network, security groups, and cloud budget alerts. | M2-01 | 2 | Week 7 | AWS environments created with billing alerts set up to avoid surprise costs.
M2-03 | User Authentication & Security (Cognito) | Set up user login/signup using AWS Cognito, API keys, and rate limits to block spam. | M2-02 | 3 | Week 8 | Users can log in securely and API blocks unauthenticated users.
M2-04 | Dockerize App & Deploy to ECS | Wrap app into Docker containers and deploy to AWS ECS/Fargate for automatic container running. | M2-02; M1-20 | 3 | Week 8 | Backend runs live in AWS container environment with auto-restart.
M2-05 | Cloud Database Setup (Aurora PostgreSQL) | Set up AWS Aurora/RDS Postgres database for structured data with automated daily backups. | M2-01; M2-02 | 3 | Week 9 | Cloud database connected to app with backup policies active.
M2-06 | Cloud Chat Storage (DynamoDB) | Store chat history and active sessions in AWS DynamoDB for fast, scalable access. | M2-01; M1-12 | 3 | Week 9 | Chat histories saved and loaded instantly from cloud NoSQL database.
M2-07 | Cloud Cache Setup (ElastiCache Redis) | Deploy AWS ElastiCache Redis to speed up frequent queries and manage session locks. | M2-03; M2-06 | 2 | Week 9 | Caching active in cloud environment with zero downtime on cache reset.
M2-08 | File Upload & Processing (S3 + Lambda) | Set up AWS S3 buckets for file storage and trigger automatic document ingestion when files are uploaded. | M2-02; M1-17 | 2 | Week 10 | Uploading a file to S3 automatically parses and indexes content.
M2-09 | Cloud Vector Search (OpenSearch / Bedrock KB) | Set up cloud vector store (OpenSearch or Bedrock Knowledge Base) for high-performance RAG search. | M2-08 | 3 | Week 10 | Fast, secure document retrieval operating at cloud scale.
M2-10 | AWS Bedrock AI Integration | Connect AI agents to AWS Bedrock to access Claude, Llama, or Titan models securely. | M2-04; M2-09 | 3 | Week 11 | AI agents pull responses directly from AWS Bedrock API.
M2-11 | Smart AI Model Selection Logic | Route simple queries to cheap/fast models and complex tasks to high-tier AI models to save money. | M2-10; M2-03 | 2 | Week 11 | Cost-saving router sends easy tasks to cheaper models automatically.
M2-12 | Serverless Tool Functions (AWS Lambda) | Deploy external tool integrations (email, payment check, CRM) as standalone AWS Lambda functions. | M2-03; M2-05; M2-10 | 3 | Week 12 | Tools run as independent cloud functions with full audit logs.
M2-13 | Background Job Queue (SQS / EventBridge) | Set up AWS SQS queue to process heavy background workflows without locking the web server. | M2-04; M2-12 | 3 | Week 12 | Long-running tasks complete asynchronously in the background.
M2-14 | Secrets & Key Management (KMS / Secrets Manager) | Store database passwords and API keys in AWS Secrets Manager with encrypted KMS keys. | M2-02; M2-03 | 2 | Week 12 | Zero plain text passwords in codebase; auto-loaded from cloud secret store.
M2-15 | Cloud Logging & Monitoring (CloudWatch) | Set up dashboard to monitor server CPU, memory, API latency, error counts, and AI token costs. | M2-04; M2-10; M2-13 | 3 | Week 13 | Central dashboard shows system health, errors, and live cost metrics.
M2-16 | Audit & Activity Logs | Record all user actions, AI decisions, and system events into non-editable audit logs for safety. | M2-06; M2-14; M2-15 | 2 | Week 13 | Complete historical trail of AI inputs, outputs, and system actions stored.
M2-17 | AWS Cost Estimator & Model | Calculate expected monthly AWS bill for compute, AI tokens, databases, and bandwidth. | M2-02; M2-10 through M2-16 | 2 | Week 14 | Detailed breakdown of monthly cloud expenses for low/high traffic.
M2-18 | Cost Guardrails & Budget Alerts | Set up automatic spending limits that trigger alerts or switch to cheaper models if cost spikes. | M2-11; M2-17 | 2 | Week 14 | Automated email alerts trigger if daily spending exceeds limit.
M2-19 | Data Migration & Cloud Test Run | Migrate local test data to AWS, run side-by-side test chats, and test rollback procedures. | M2-05 through M2-09; M2-16 | 3 | Week 15 | All local test data present in cloud; system verified functional.
M2-20 | AWS Staging Testing & Approval | Perform full end-to-end testing in Staging environment before opening to real users. | M2-01 through M2-19 | 3 | Week 16 | Staging environment approved with zero critical bugs.
51
¦-> Milestone 3 - Production & Launch Readiness
Task ID | Simplified Task Name | POC Details & Work Description | Dependencies | Est. Days (POC) | ETA Timeline | Acceptance Criteria
M3-01 | Define Performance & Uptime Targets (SLOs) | Define simple goal targets: 99.5% uptime, <2s chat response time, and accuracy standards. | M2-20 | 2 | Week 17 | Documented goals for speed, uptime, and AI response quality.
M3-02 | Automated Testing Pipeline (CI) | Set up GitHub Actions to automatically run unit and integration tests on every code push. | M2-20 | 2 | Week 17 | Automated test suite blocks broken code from merging.
M3-03 | AI Quality & Benchmark Testing | Create a test suite of 50+ common user questions to automatically test AI accuracy and tone. | M3-02 | 3 | Week 18 | Automated test suite scores AI response accuracy against expected answers.
M3-04 | Document Search Quality Test | Test document search accuracy to ensure AI gives true facts with correct page citations. | M3-03 | 2 | Week 18 | RAG evaluation pipeline checks citation accuracy and prevents hallucinations.
M3-05 | Prompt & Model Drift Check | Compare AI quality and output costs whenever prompts or underlying AI models are updated. | M3-03; M3-04 | 2 | Week 18 | Prompt updates verified against benchmarks before release.
M3-06 | Security Red-Teaming (Hacker Test) | Attempt to hack the AI with jailbreaks, secret leakage prompts, and bad input injection. | M3-02; M3-03 | 3 | Week 19 | All tested prompt injection hacks successfully blocked.
M3-07 | Code & Vulnerability Scanning | Run automatic scanners for code bugs, dependency security flaws, and open permissions. | M2-14; M3-02 | 2 | Week 19 | Zero critical security vulnerabilities detected in automated scan.
M3-08 | Load & Traffic Stress Testing | Simulate 50+ simultaneous users chatting with the AI to verify server auto-scaling under load. | M3-01; M3-02 | 3 | Week 20 | System handles peak simulated user traffic smoothly without crashing.
M3-09 | System Recovery & Failure Testing | Test what happens if database drops or API fails to ensure graceful error messages. | M3-08 | 2 | Week 20 | App shows friendly user error and recovers automatically on reboot.
M3-10 | Backup & Restore Verification | Perform a full test restore of database and chat files to ensure no data is lost in a disaster. | M2-05; M2-06; M2-08 | 2 | Week 21 | Verified full database backup restore in under 30 minutes.
M3-11 | Data Privacy & User Deletion Test | Verify 'Delete My Account' feature completely removes user data and chat history from cloud. | M2-06; M2-16 | 2 | Week 21 | User data deletion request leaves zero trace in active databases.
M3-12 | Human Feedback & Quality Review | Build simple dashboard for admin team to thumbs up/down AI answers and improve prompts. | M3-03 through M3-06 | 2 | Week 22 | Admins can view flagged user responses and tweak AI instructions.
M3-13 | Automated Deployment Pipeline (CD) | Automate code deployment so pushing to `main` updates staging/production automatically. | M3-02; M3-07 | 3 | Week 22 | One-click deployment with automatic rollback on error.
M3-14 | Feature Flags & Gradual Rollout | Add feature flags to release new features to 10% of users first before full rollout. | M3-01; M3-13 | 2 | Week 23 | Features can be toggled on/off instantly without redeploying code.
M3-15 | Operational Dashboards & Alerts | Configure real-time Slack/Email alerts when system errors spike or server goes down. | M2-15; M3-01 | 2 | Week 23 | Alerts ping developer Slack channel immediately on critical error.
M3-16 | System Playbook & Incident Steps | Write simple step-by-step guides for common issues (server reboot, high latency, secret rotation). | M3-09; M3-10; M3-15 | 2 | Week 24 | Clear troubleshooting guide ready for technical team on-call.
M3-17 | Human Support Escalation Workflow | Connect chat app to live customer support (Slack/Zendesk) when AI cannot help user. | M2-13; M3-12 | 2 | Week 24 | Seamless handoff from AI chat to live human support agent.
M3-18 | Frontend Hardening & Polish | Polish mobile layout, fix browser glitches, add error toasts, and improve loading speed. | M1-19; M3-02; M3-11 | 2 | Week 25 | Web UI works fast and smooth across desktop, tablet, and mobile.
M3-19 | Final Launch Readiness Checklist | Complete final security, cost, legal, and engineering sign-off meeting before go-live. | M3-01 through M3-18 | 2 | Week 26 | Final go-live sign-off completed by tech lead and product lead.
M3-20 | Production Go-Live & Post-Launch Support | Deploy to live production domain, open to real users, and monitor closely for first 2 weeks. | M3-19 | 3 | Weeks 27-28 | App is live, stable, serving real users, and monitored actively.
45