## Master Task List (All 60)
AI Assistant POC - Complete 60-Task Implementation Roadmap
Full list of all tasks grouped into Milestone 1, Milestone 2, and Milestone 3.
Milestone 1 - Local Implementation
Milestone Phase | Task ID | Task Name (Simplified) | Clear Task Details & Purpose | Est. Dev Days | Dependencies | Target ETA | Acceptance Criteria (Definition of Done)
Milestone 1 - Local Implementation | M1-01 | Baseline Audit & Requirements Matrix | Map current prototype against final target architecture; document gaps and list required local components. | 2 | None | Week 1 | Approved gap matrix and clear plan connecting components to tasks.
Milestone 1 - Local Implementation | M1-02 | Codebase Cleanup & Standardization | Set up code formatting, auto-checks (linting), type hints, logging, and lock library versions. | 3 | M1-01 | Week 1 | Code check and formatting scripts run smoothly without errors.
Milestone 1 - Local Implementation | M1-03 | Project Folder Restructuring | Organize code into clean folders: frontend, backend, shared, tests, scripts, and config. | 2 | M1-01 | Week 1 | App starts easily using simple terminal commands with clean code imports.
Milestone 1 - Local Implementation | M1-04 | Centralized Configuration Management | Store settings (database URLs, API keys, paths, feature flags) in one central place using environment variables. | 2 | M1-02 | Week 1 | No hardcoded file paths; app works regardless of where it is run from.
Milestone 1 - Local Implementation | M1-05 | FastAPI Core Service Setup | Build core FastAPI backend with health checks, API routing, standard error handling, and data models. | 3 | M1-03 | Week 2 | FastAPI service exposes working health check and chat endpoints.
Milestone 1 - Local Implementation | M1-06 | Local Service Module Boundaries | Separate backend modules (API, Orchestrator, Agent, Memory, Knowledge, Tools, Safety, Logs) to prevent tangled code. | 4 | M1-03; M1-04 | Week 2 | Each module has a stable interface and isolated automated tests.
Milestone 1 - Local Implementation | M1-07 | API Conversation & Streaming Contract | Standardize API formats for live response streaming, unique request IDs, tracking headers, and structured error responses. | 3 | M1-05 | Week 2 | Invalid requests return clear error messages and every response contains tracking IDs.
Milestone 1 - Local Implementation | M1-08 | Unique Chat & Session Tracking (UUIDv7) | Add time-sortable unique IDs (UUIDv7) to every chat session and thread to track user history reliably. | 2 | M1-06; M1-07 | Week 2 | Every conversation gets a unique, chronological ID for thread tracking.
Milestone 1 - Local Implementation | M1-09 | Short-Term Chat Context Memory | Keep recent chat messages in memory while trimming older text so AI prompt token limits aren't exceeded. | 3 | M1-08 | Week 3 | Only recent relevant messages are sent to AI, staying within word limits.
Milestone 1 - Local Implementation | M1-10 | Long-Term User Memory & Retention | Store user preferences and key details across sessions with options to edit, auto-expire, or delete them. | 4 | M1-08; M1-09 | Week 3 | User preferences stay saved across sessions and respect privacy expiration rules.
Milestone 1 - Local Implementation | M1-11 | Automatic Chat History Summarization | Summarize older chat turns into short background notes so the AI retains key context without high API costs. | 3 | M1-09; M1-10 | Week 3 | Old conversations auto-summarize and AI answers remain coherent.
Milestone 1 - Local Implementation | M1-12 | Local Database & Schema Migrations | Set up local database storage with schema migrations to store user chat history and session data safely. | 4 | M1-08; M1-09 | Week 3 | Data survives app restarts and database schema updates run reproducibly.
Milestone 1 - Local Implementation | M1-13 | Model Gateway (AI Provider Switcher) | Create a single wrapper to connect to different AI models (OpenAI, Anthropic, local models) with retries and fallbacks. | 4 | M1-06; M1-07 | Week 4 | System can switch AI models easily without changing core agent logic.
Milestone 1 - Local Implementation | M1-14 | Tool & External Action Gateway | Build a secure registry for external tools (e.g., database lookup, API calls) with safety checks and error retries. | 4 | M1-06; M1-13 | Week 4 | Tools execute safely, unauthorized calls are blocked, and actions are logged.
Milestone 1 - Local Implementation | M1-15 | Input & Output Safety Controls | Add guardrails to detect prompt injection, hide sensitive personal data (PII), and block unsafe content. | 4 | M1-07; M1-13; M1-14 | Week 4 | Unsafe prompts or output are flagged, redacted, or blocked with audit logs.
Milestone 1 - Local Implementation | M1-16 | Agent Behavior & Failure Handling | Refine AI agents (Policy, Claims, Billing, Escalation) to gracefully handle missing data or unclear prompts. | 5 | M1-09; M1-13; M1-14; M1-15 | Week 5 | Agents handle errors smoothly, clarify ambiguous questions, and execute handoffs.
Milestone 1 - Local Implementation | M1-17 | Document Search & RAG Pipeline | Upload documents, split into chunks, index text vectors, and output answers backed by citations. | 5 | M1-04; M1-13; M1-15 | Week 5 | AI provides accurate answers backed by document citations and access checks.
Milestone 1 - Local Implementation | M1-18 | Local Caching & Async Event Bus | Add cache for fast repeated responses and a local background job queue for heavy asynchronous tasks. | 4 | M1-08; M1-12 | Week 5 | Common answers load instantly from cache and background failures auto-retry.
Milestone 1 - Local Implementation | M1-19 | Frontend Web UI & API Integration | Build a simple, clean chat interface showing messages, loading states, source citations, and error notifications. | 5 | M1-05; M1-07; M1-08 | Week 6 | Users can send messages, view citations, resume chats, and see live status.
Milestone 1 - Local Implementation | M1-20 | Local Testing & Setup Documentation | Write unit/integration tests and complete a step-by-step developer setup and troubleshooting guide. | 5 | M1-02 through M1-19 | Week 6 | All automated tests pass and a new developer can set up the app in under 30 mins.
Total Effort for Milestone 1 - Local Implementation |  |  |  | 71
Milestone 2 - AWS Migration
Milestone Phase | Task ID | Task Name (Simplified) | Clear Task Details & Purpose | Est. Dev Days | Dependencies | Target ETA | Acceptance Criteria (Definition of Done)
Milestone 2 - AWS Migration | M2-01 | AWS Architecture & Component Mapping | Plan how local backend, memory, and database services map to AWS cloud services (ECS, S3, RDS, DynamoDB). | 3 | M1-20 | Week 7 | Architecture design document approved with local-to-AWS service mapping.
Milestone 2 - AWS Migration | M2-02 | AWS Account & Environment Foundation | Set up AWS environments (Dev, Staging, Prod) with network VPCs, security rules, tagging, and budget limits. | 4 | M2-01 | Week 7 | AWS environments are isolated, reproducible, and budget-monitored.
Milestone 2 - AWS Migration | M2-03 | User Authentication & API Gateway Security | Set up Cognito user login, IAM roles, and API Gateway with WAF to secure and rate-limit web traffic. | 5 | M2-02 | Week 8 | Only authenticated users can call protected APIs with proper tenant isolation.
Milestone 2 - AWS Migration | M2-04 | Docker Container Cloud Deployment (ECS) | Package backend services into Docker containers and deploy on AWS ECS/Fargate with auto-scaling. | 4 | M2-02; M1-20 | Week 8 | Services deploy independently and automatically recover from container crashes.
Milestone 2 - AWS Migration | M2-05 | AWS Cloud Database Setup (Aurora PostgreSQL) | Migrate relational database to AWS Aurora PostgreSQL with automated backups and replication. | 5 | M2-01; M2-02 | Week 9 | Cloud database is running, integrated with backend, and backed up automatically.
Milestone 2 - AWS Migration | M2-06 | DynamoDB Chat History & State Store | Store active chat sessions, user summaries, and conversation history in AWS DynamoDB. | 5 | M2-01; M1-12 | Week 9 | Chat history reads/writes fast, scales automatically, and supports session recovery.
Milestone 2 - AWS Migration | M2-07 | ElastiCache (Redis) Caching Layer | Deploy AWS ElastiCache Redis for fast temporary data storage, lock management, and API rate limiting. | 3 | M2-03; M2-06 | Week 9 | Caching reduces database load and gracefully degrades if cache misses occur.
Milestone 2 - AWS Migration | M2-08 | S3 Document Storage & Ingestion Trigger | Set up AWS S3 buckets for file uploads, triggering automatic document indexing upon upload. | 4 | M2-02; M1-17 | Week 10 | Uploading files to S3 triggers repeatable, versioned, and monitored ingestion.
Milestone 2 - AWS Migration | M2-09 | Managed Vector Search Platform | Set up AWS OpenSearch or Bedrock Knowledge Bases for document retrieval and citation lookup. | 5 | M2-08 | Week 10 | Vector search returns relevant, access-controlled context with clear source links.
Milestone 2 - AWS Migration | M2-10 | AWS Bedrock Model Integration Gateway | Connect backend agents to AWS Bedrock to access foundation models (Claude/Llama) with backup routing. | 5 | M2-04; M2-09 | Week 11 | Backend calls Bedrock models securely with automated fallback handling.
Milestone 2 - AWS Migration | M2-11 | Three-Tier Model Routing Strategy | Route simple queries to cheap models and complex queries to premium models based on user tier. | 5 | M2-10; M2-03 | Week 11 | Queries automatically choose the cost-optimal model tier without manual intervention.
Milestone 2 - AWS Migration | M2-12 | Serverless Tool Execution (AWS Lambda) | Deploy external integration tools as AWS Lambda functions with granular security permissions. | 5 | M2-03; M2-05; M2-10 | Week 12 | Tools run as lightweight serverless functions with full audit logs.
Milestone 2 - AWS Migration | M2-13 | Async Queue Workflows (SQS & EventBridge) | Set up SQS message queues and EventBridge for background job processing, retries, and dead-letter queues. | 5 | M2-04; M2-12 | Week 12 | Heavy tasks process asynchronously without blocking real-time user requests.
Milestone 2 - AWS Migration | M2-14 | Secrets Manager & Encryption Setup (KMS) | Store API keys securely in AWS Secrets Manager and enable KMS key encryption across all data stores. | 3 | M2-02; M2-03 | Week 12 | No plain-text credentials in code; all secrets loaded dynamically via KMS.
Milestone 2 - AWS Migration | M2-15 | Cloud Monitoring & Centralized Logs | Set up AWS CloudWatch and OpenTelemetry to log API speed, agent calls, model usage, and errors. | 5 | M2-04; M2-10; M2-13 | Week 13 | Developers can trace a request's full journey across services on a live dashboard.
Milestone 2 - AWS Migration | M2-16 | Cloud Audit & Compliance Storage | Store immutable records of AI agent decisions, tool calls, and user actions for security compliance. | 4 | M2-06; M2-14; M2-15 | Week 13 | Security auditors can review full conversation logs and operational decisions.
Milestone 2 - AWS Migration | M2-17 | Cloud Cost Breakdown & Financial Model | Calculate expected monthly AWS bills across compute, AI tokens, databases, storage, and networking. | 4 | M2-02; M2-10 through M2-16 | Week 14 | Detailed financial estimation model covering low, average, and peak usage traffic.
Milestone 2 - AWS Migration | M2-18 | Cost Controls & Token Quotas | Set spending limits, per-tenant token usage caps, and automated alerts to prevent unexpected AWS bills. | 3 | M2-11; M2-17 | Week 14 | Usage spikes trigger budget alerts and automatic model downgrade controls.
Milestone 2 - AWS Migration | M2-19 | Data Migration & Cutover Rehearsal | Migrate local test data to AWS and run a full rehearsal of switching operations from local to cloud. | 5 | M2-05 through M2-09; M2-16 | Week 15 | Cloud environment produces identical test results to local; rollback plan verified.
Milestone 2 - AWS Migration | M2-20 | AWS Staging Acceptance Testing | Run functional, performance, security, and failure recovery tests in AWS Staging environment. | 5 | M2-01 through M2-19 | Week 16 | Staging passes all stability, latency, security, and functional acceptance gates.
Total Effort for Milestone 2 - AWS Migration |  |  |  | 87
Milestone 3 - Production Readiness
Milestone Phase | Task ID | Task Name (Simplified) | Clear Task Details & Purpose | Est. Dev Days | Dependencies | Target ETA | Acceptance Criteria (Definition of Done)
Milestone 3 - Production Readiness | M3-01 | Production SLOs & Alert Thresholds | Define strict targets for API speed, uptime (99.9%), AI response accuracy, and operational alerts. | 3 | M2-20 | Week 17 | Target response times (<2s) and uptime targets (99.9%) formally documented.
Milestone 3 - Production Readiness | M3-02 | Automated CI/CD Testing Strategy | Set up automated test pipelines running unit, integration, and security checks on every code submission. | 4 | M2-20 | Week 17 | Code cannot be merged into production branch unless all automated tests pass.
Milestone 3 - Production Readiness | M3-03 | AI Agent Accuracy Benchmarking | Create test datasets to measure if AI agents route questions correctly and output high-quality answers. | 4 | M3-02 | Week 18 | AI responses scored against verified golden answers with >90% accuracy target.
Milestone 3 - Production Readiness | M3-04 | RAG Retrieval Quality & Citation Testing | Evaluate document retrieval recall, citation accuracy, and handling of missing context. | 4 | M3-03 | Week 18 | RAG pipeline passes factual grounding and citation accuracy benchmarks.
Milestone 3 - Production Readiness | M3-05 | Prompt & Model Quality Checks | Compare response quality and cost whenever prompts or AI model versions are modified. | 4 | M3-03; M3-04 | Week 18 | Prompt updates require passing quality checks to prevent unexpected degradation.
Milestone 3 - Production Readiness | M3-06 | AI Safety & Red-Teaming Tests | Simulate security attacks (prompt injection, jailbreaks, data leaks) to test guardrails. | 5 | M3-02; M3-03 | Week 19 | All identified safety vulnerabilities patched before production launch.
Milestone 3 - Production Readiness | M3-07 | Security & Vulnerability Scanning | Perform automated code scanning, dependency checks, penetration tests, and IAM role reviews. | 5 | M2-14; M3-02 | Week 19 | Zero critical or high security vulnerabilities remain unmitigated.
Milestone 3 - Production Readiness | M3-08 | Load & Capacity Stress Testing | Simulate hundreds of simultaneous active users to verify system handles high traffic without breaking. | 5 | M3-01; M3-02 | Week 20 | System automatically scales up under peak traffic while maintaining speed targets.
Milestone 3 - Production Readiness | M3-09 | Resilience & Failure Injection Testing | Intentionally disconnect databases, caches, or AI model endpoints to test auto-recovery. | 4 | M3-08 | Week 20 | App degrades gracefully, retries safely, and preserves user data during outages.
Milestone 3 - Production Readiness | M3-10 | Disaster Recovery & Backup Drills | Validate cross-region data backups and test restoring system state within target timeframe. | 4 | M2-05; M2-06; M2-08 | Week 21 | System restored successfully within 1-hour Recovery Time Objective (RTO).
Milestone 3 - Production Readiness | M3-11 | Data Privacy & Account Deletion Verification | Verify user consent management, data retention limits, and automated account wiping features. | 4 | M2-06; M2-16 | Week 21 | Data deletion requests erase all user history in compliance with privacy rules.
Milestone 3 - Production Readiness | M3-12 | Human Review & Feedback Dashboard | Build simple internal tool for team members to rate AI answers and flag low-quality responses. | 4 | M3-03 through M3-06 | Week 22 | Operations team can review user-flagged chats and continuously tune performance.
Milestone 3 - Production Readiness | M3-13 | Automated Release Pipeline (CI/CD) | Build automated deployment pipeline to push code safely to production with single-click rollback. | 5 | M3-02; M3-07 | Week 22 | Deployments to production are automated, audited, and rollback-ready.
Milestone 3 - Production Readiness | M3-14 | Canary & Feature Flag Rollout | Deploy new software versions to a small group of users first before full public release. | 4 | M3-01; M3-13 | Week 23 | Feature flags allow disabling broken features instantly without redeploying code.
Milestone 3 - Production Readiness | M3-15 | Operational Dashboards & Live Alerting | Finalize CloudWatch dashboards showing system speed, active chats, error rates, and live costs. | 3 | M2-15; M3-01 | Week 23 | Real-time visual monitoring active with instant threshold alert notifications.
Milestone 3 - Production Readiness | M3-16 | On-Call Runbooks & Operational Guides | Write step-by-step troubleshooting guides for common incident scenarios and system failures. | 3 | M3-09; M3-10; M3-15 | Week 24 | Engineers test runbooks during simulated incident drills.
Milestone 3 - Production Readiness | M3-17 | Human Support Queue Handoff | Connect complex AI customer queries to human support agents with full conversation history. | 3 | M2-13; M3-12 | Week 24 | Support team receives complete chat context when an AI conversation is escalated.
Milestone 3 - Production Readiness | M3-18 | Frontend Production Hardening | Fix UI edge-cases, ensure mobile browser compatibility, refine streaming UX, and polish controls. | 4 | M1-19; M3-02; M3-11 | Week 25 | Frontend UI works smoothly across desktop and mobile devices.
Milestone 3 - Production Readiness | M3-19 | Final Go-Live Sign-Off Review | Conduct formal review with Engineering, Product, Security, and Operations leadership. | 4 | M3-01 through M3-18 | Week 26 | Formal production release checklist signed off by key stakeholders.
Milestone 3 - Production Readiness | M3-20 | Production Launch & Stabilization | Execute final public release, monitor live traffic, resolve initial launch issues, and transfer support. | 5 | M3-19 | Weeks 27-28 | Production launch completed successfully with stable operational metrics.
Total Effort for Milestone 3 - Production Readiness |  |  |  | 81

## Project Dashboard
Startup AI Assistant POC - Executive Dashboard
Summary of milestones, effort estimations, task counts, and execution timelines.
Milestone Overview & Key Metrics
Milestone Phase | Total Tasks | Est. Dev Days | Timeline Window | Primary Scope Focus
Milestone 1 - Local Implementation | 21 | 71 | Weeks 1 - 6 | Local Architecture, Core FastAPI, Safety, RAG & Memory POC
Milestone 2 - AWS Migration | 21 | 87 | Weeks 7 - 16 | Cloud Scaling, ECS Containers, Bedrock AI, DynamoDB & Security
Milestone 3 - Production Readiness | 21 | 81 | Weeks 17 - 28 | Testing, AI Benchmarking, Red-Teaming, CI/CD & Launch
Total Project Scope | 63 | 239 | 28 Weeks Total | End-to-End Local Prototype to Cloud Launch