## Task Register
Multi-Agent AI Platform — Production Delivery Task Register
Task ID | Task / Activity | Scope / Acceptance Criteria | Deliverable / Exit Criteria | Task Description | Workstream | Area | Priority | Owner | Status | Start Date | Due Date | Phase
1 | Define end-to-end multi-agent architecture | LangGraph supervisor → specialist agents → RAG/tools → HITL → final response; define service boundaries | Architecture diagram + design doc |  | Architecture | Architecture & Design | High | Architect | Not Started | TBD | TBD | Foundation
2 | Define LangGraph state and orchestration | Define shared state, agent routing, checkpoints, retries, fallbacks, and termination conditions | State schema + graph design |  | Architecture | Architecture & Design | High | AI Engineer | Not Started | TBD | TBD | Foundation
3 | Build FastAPI application structure | Create API layers, routers, services, schemas, exception handling and configuration management | Running FastAPI service |  | API | FastAPI | High | Backend Engineer | Not Started | TBD | TBD | Foundation
4 | Implement JWT authentication | Login/token validation, token expiry, protected endpoints, middleware/dependencies | Authenticated API endpoints |  | Security | Authentication | Critical | Backend Engineer | Not Started | TBD | TBD | Security
5 | Design RBAC model | Define users, roles, permissions, agent/tool access policies and resource-level authorization | RBAC matrix + policy model |  | Security | RBAC | Critical | Backend + AI Engineer | Not Started | TBD | TBD | Security
6 | Implement user-aware tool gateway | Validate JWT/RBAC before every tool call; authorize tool, action, resource and parameters | Secure tool gateway |  | Tools | Tool Gateway | Critical | AI Engineer | Not Started | TBD | TBD | Security
7 | Implement tool execution layer | Centralize tool registration, validation, execution, timeout, retries, audit logs and error handling | Tool registry + executor |  | Tools | Tool Gateway | High | AI Engineer | Not Started | TBD | TBD | Core
8 | Build supervisor agent | Route requests to specialist agents, manage state, retries, delegation and final synthesis | Working supervisor graph |  | Agents | Supervisor | High | AI Engineer | Not Started | TBD | TBD | Core
9 | Build specialist agent framework | Create reusable agent pattern for domain agents with prompts, tools, policies and output schemas | Agent template |  | Agents | Specialist Agents | High | AI Engineer | Not Started | TBD | TBD | Core
10 | Integrate Claude Sonnet | Integrate Claude Sonnet through Amazon Bedrock with centralized model configuration | Bedrock LLM integration |  | LLM | AWS Bedrock | High | AI Engineer | Not Started | TBD | TBD | Core
11 | Implement model routing | Route workloads across Claude/SLLMs based on task, latency, cost, context and fallback policy | Model routing layer |  | LLM | LLM Gateway | Medium | AI Engineer | Not Started | TBD | TBD | Optimization
12 | Implement Bedrock input guardrails | Validate prompt injection/jailbreak, toxicity, sensitive content and policy violations before agent execution | Input validation flow |  | Guardrails | Input Guardrails | Critical | AI Engineer | Not Started | TBD | TBD | Security
13 | Implement Bedrock output guardrails | Validate policy compliance, unsafe content, PII/data leakage, quality and response constraints before returning output | Output validation flow |  | Guardrails | Output Guardrails | Critical | AI Engineer | Not Started | TBD | TBD | Security
14 | Implement Redis runtime memory | Store conversation/session state, recent messages, transient agent context and TTL-based data | Redis memory integration |  | Memory | Short-Term Memory | High | Backend + AI Engineer | Not Started | TBD | TBD | Core
15 | Implement PostgreSQL memory | Persist durable user preferences, conversation summaries, facts and business memory with user/tenant isolation | PostgreSQL memory schema |  | Memory | Long-Term Memory | High | Backend Engineer | Not Started | TBD | TBD | Core
16 | Design memory lifecycle | Define what is stored, TTL, summarization, retrieval, deletion, privacy and memory boundaries | Memory policy |  | Memory | Memory Policy | High | AI + Security | Not Started | TBD | TBD | Security
16 | Select embedding model | Select production embedding model based on semantic retrieval quality, dimensions, latency, cost, multilingual needs and AWS compatibility | Embedding model decision + benchmark |  | Memory | Embedding Memory | High | AI Engineer | Not Started | TBD | TBD | Core
17 | Generate embeddings for summaries | Create embeddings whenever conversation/session summaries are created or updated | Summary embedding pipeline |  | Memory | Summary Embeddings | High | AI Engineer | Not Started | TBD | TBD | Core
18 | Store summary embeddings | Persist summary text + embedding + user/tenant/session metadata in vector-capable storage for real-time retrieval | Vector memory store |  | Memory | Vector Retrieval | High | AI + Backend Engineer | Not Started | TBD | TBD | Core
19 | Implement semantic memory retrieval | Retrieve top-K relevant historical summaries using similarity search and metadata/RBAC filters at runtime | Realtime semantic memory retrieval |  | Memory | Vector Retrieval | High | AI Engineer | Not Started | TBD | TBD | Core
20 | Implement summary update strategy | Define when to summarize, re-embed, merge, expire, delete and version memories | Memory lifecycle policy |  | Memory | Memory Lifecycle | High | AI + Backend Engineer | Not Started | TBD | TBD | Core
22 | Integrate Langfuse tracing | Trace LLM calls, prompts, agent steps, tool calls, latency, token usage, cost and errors | Langfuse traces |  | Observability | Langfuse | High | AI Engineer | Not Started | TBD | TBD | Observability
23 | Implement OpenTelemetry | Add distributed tracing/metrics across FastAPI, LangGraph, tools, Redis, PostgreSQL and Bedrock | OTel instrumentation |  | Observability | OpenTelemetry | High | Platform Engineer | Not Started | TBD | TBD | Observability
24 | Implement request/trace correlation | Propagate request_id, user_id/tenant_id, trace_id and LangGraph thread_id across all services | End-to-end correlation |  | Observability | Correlation | High | Backend + Platform | Not Started | TBD | TBD | Observability
25 | Implement retries and timeouts | Add bounded retries, exponential backoff, circuit breakers and tool/LLM timeout policies | Resilient execution |  | Reliability | Agent Runtime | High | AI Engineer | Not Started | TBD | TBD | Reliability
26 | Implement HITL escalation | Escalate low confidence, policy violations, high-risk tools and failed agent paths to human review | HITL workflow |  | Reliability | Human Escalation | High | AI Engineer | Not Started | TBD | TBD | Reliability
27 | Create production data model | Users, roles, permissions, conversations, messages, memory, audit events and agent execution metadata | DB schema + migrations |  | Data | PostgreSQL | High | Backend Engineer | Not Started | TBD | TBD | Foundation
28 | Test agents and services | Unit tests for graph nodes, routing, guardrails, JWT/RBAC, memory and tool gateway | Automated unit suite |  | Testing | Unit Tests | High | QA + Engineers | Not Started | TBD | TBD | Quality
29 | Create agent evaluation suite | Golden datasets, task success, groundedness, tool correctness, safety and regression evaluations | Evaluation framework |  | Testing | Evaluation | High | AI Engineer | Not Started | TBD | TBD | Quality
30 | Test prompt injection and authorization | Adversarial tests for jailbreaks, RBAC bypass, IDOR, tool abuse, PII leakage and malicious inputs | Security test report |  | Testing | Security Testing | Critical | Security + AI Engineer | Not Started | TBD | TBD | Security
31 | Performance/load test APIs and agents | Measure concurrency, p95/p99 latency, throughput, Redis/Postgres behavior and Bedrock bottlenecks | Performance report |  | Testing | Load Testing | Medium | QA + Platform | Not Started | TBD | TBD | Performance
32 | Set up CI/CD pipeline | Lint, type checks, tests, security scan, image build, deployment and environment promotion | CI/CD pipeline |  | DevOps | CI/CD | High | DevOps | Not Started | TBD | TBD | Deployment
33 | Deploy FastAPI and agent runtime | Deploy production API/agent services using AWS managed runtime with secure networking and IAM | Production deployment |  | AWS | Deployment | Critical | Cloud + DevOps | Not Started | TBD | TBD | Deployment
34 | Configure IAM and secrets | Least-privilege IAM, Bedrock permissions, database/Redis secrets, KMS and environment configuration | IAM + secrets setup |  | AWS | Secrets & IAM | Critical | Cloud + Security | Not Started | TBD | TBD | Security
35 | Conduct UAT and production readiness | Validate functional, security, observability, cost, latency, failure and rollback criteria | UAT sign-off + go-live checklist |  | Release | UAT | Critical | Tech Lead + QA | Not Started | TBD | TBD | Release

## Architecture Summary
Architecture Delivery Summary
Project | Production Multi-Agent AI Platform
Core orchestration | LangGraph Supervisor + Specialist Agents
API | FastAPI + JWT Authentication
Authorization | RBAC + User-aware Tool Gateway
LLM | AWS Bedrock Claude Sonnet
Guardrails | AWS Bedrock Input + Output Guardrails
Short-term memory | Redis
Long-term memory | PostgreSQL
Observability | Langfuse + OpenTelemetry
Primary focus | Security, reliability, observability, scalability
Semantic memory | Conversation summaries → embedding model → vector store → metadata/RBAC-filtered top-K retrieval → LangGraph runtime context
Embedding model | Production choice to be benchmarked for retrieval quality, latency, cost, dimensions and AWS compatibility
Memory flow | Short-term: Redis ¦ Long-term: PostgreSQL ¦ Semantic summary retrieval: embedding + vector search

## Sheet1
Stack: FastAPI + JWT/RBAC + LangGraph + AWS Bedrock Claude Sonnet + Bedrock Guardrails + Redis + PostgreSQL + Embedding Model + Vector Memory + Langfuse + OpenTelemetry